Engineering Review Comments – One River Run Hotel Building Permit G&E

From:	Paul Geiger –Engineer 1

To:	Scott Russell, Todd Morgan

Cc:	Robert Jacobs, County Engineer and Road & Bridge Director

Re:	One River Run Building Permit B20-0201

Keystone, Summit County, Colorado

Date:	July 2020 - August 12, 2020

The following are comments regarding the above referenced Building Permit submittal. Any reference to ‘The Code’ shall refer to the Summit County Land Use and Development Code unless otherwise noted.

Prior to issuance of the County Grading & Excavation (G&E) Permit associated with this Building Permit, the following items will need to be submitted to the County for review and approval:

- The amended Subdivision Exemption Plat reflecting the final location of all utility, pedestrian, vehicular and emergency access easements required by the Site Plan shall be approved and recorded. – In process by the County Building Department.

- Wetlands Disturbance Permit Application and Mitigation Report and Plan. – Received, to be reviewed by the County Engineering Department.

- Final Drainage Report, stamped and signed by a State of Colorado Licensed Engineer. The submitted Grading and Drainage Plans will need to be reviewed for conformance with this Report once it is submitted. – Received, to be reviewed by the Engineering Department.

- A Site Improvements Agreement accepted by the County and recorded, with a full financial guarantee provided for all required site improvements. – Not provided, please confer with the County Planning Department.

- Grading & Excavation Permits shall be submitted and approved for the Powerline Lot Phase II improvements, to be completed prior to the Hunki Dori parking lot being displaced by permanent construction of the One River Run Hotel. A Site Improvements Agreement and Financial Guarantee for the Powerline Phase II work shall also be submitted and approved. – Not yet provided.

- Engineered Plans for the proposed bus circulation improvements at the Montezuma Road and Ida Belle Drive intersection must be submitted, reviewed, and approved by the County Engineering and Opens Space & Trails departments. Improvements to the Montezuma Road and Ida Belle Drive shall include, but are not limited to, a right turn lane off Montezuma Road onto Ida Belle Drive, right-turn gate controlled bus access from Montezuma Road onto Ida Belle Drive, a pedestrian cross walk, striping and pavement marking as may be necessary, as well as signage connecting the Rec Path across Ida Belle Drive. These improvements shall be completed prior to release of financial guarantees for the Powerline Lot Phase II improvements. – Not yet provided.