Engineering Review Comments – One River Run Hotel Building Permit G&E

From:	Paul Geiger –Engineer 1

To:	Scott Russell, Todd Morgan

Cc:	Robert Jacobs, County Engineer and Road & Bridge Director

Re:	One River Run Building Permit B20-0201

Keystone, Summit County, Colorado

Date:	July 2020 - December 2021

The following are comments regarding the above referenced Building Permit submittal. Any reference to ‘The Code’ shall refer to the Summit County Land Use and Development Code unless otherwise noted.

Prior to issuance of the County Grading & Excavation (G&E) Permit associated with this Building Permit, the following items will need to be submitted to the County for review and approval:

- The amended Subdivision Exemption Plat reflecting the final location of all utility, pedestrian, vehicular and emergency access easements as required by the proposed Site Plan shall be approved and recorded.

- Please work with the County Planning Department to complete this requirement.

- Wetlands Disturbance Plan Application and Mitigation Report and Plan have been provided.

The Wetlands Disturbance Plan has been reviewed and can be approved. Per the requirements of Code Section 7105.06, a financial guarantee must be provided to ensure completion of the wetlands mitigation and three year’s successful monitoring period.

- Final Drainage Report, stamped and signed by a State of Colorado Licensed Engineer. The submitted Grading and Drainage Plans will need to be reviewed for conformance with this Report once it is submitted.  – The Drainage Report and Plans have been submitted and reviewed; they align with the Building Permit Site Plans, and are in conformance with Chapter 7 Water Quality Control Regulations.

- A Site Improvements Agreement must be provided, accepted by the County and recorded, with a full financial guarantee provided for all required site improvements. - Please work with the County Planning Department to complete this requirement.

- Grading & Excavation Permits shall be submitted and approved for the Powerline Lot Phase II improvements, to be completed prior to the Hunki Dori parking lot being displaced by permanent construction of the One River Run Hotel. A Site Improvements Agreement and Financial Guarantee for the Powerline Phase II work shall also be submitted and approved.  – Powerline Lot Phase 2 and 3 improvements have been substantially completed.

- Engineered Plans for the proposed bus circulation improvements at the Montezuma Road and Ida Belle Drive intersection must be submitted, reviewed, and approved by the County Engineering and Open Space & Trails departments.  Improvements to the Montezuma Road and Ida Belle Drive shall include, but are not limited to, a right turn lane off Montezuma Road onto Ida Belle Drive, gate controlled bus access from Montezuma Road onto Ida Belle Drive, a pedestrian cross walk, striping and pavement marking as may be necessary, as well as signage connecting the Rec Path across Ida Belle Drive.

Engineered Plans for required improvements to Montezuma Road at the Powerline Lot / Independence Road intersection must be submitted and approved as part of a County Road & Bridge Right-of-Way Permit.  All Montezuma Road improvements shall be completed prior to the Hunki Dori parking lot being permanently displaced by construction of the One River Run Hotel.

– Plans for both Montezuma Road improvements have not been submitted or reviewed for final approval/permit issuance.  These plans must be submitted, approved/permitted, and the corresponding improvements completed before the permanent displacement of the Hunki Dori parking lot, prior to the Keystone 2022-2023 ski season.